## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
EatAndShare Gantt Chart
Selin Birgul and Andrias Zelele |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | #VALUE! |  |  |  |  | November | [27 empty] | December
20 | time axis 2025-11-04 to 2025-12-29
Milestone description | Column1 | Assigned to | Progress | Start | Days | time axis 2025-11-04 to 2025-12-29
Project development
Create Git Repository | Med Risk | Both | 100% | 2025-09-02 | 2
Login and Create Account page design | Low Risk | Andrias | 100% | 2025-09-05 | 7
create gantt chart | Low Risk | Selin | 100% | 2025-09-05 | 3 | 2025-11-11: 0
User recipe uploading page design | Med Risk | Selin | 100% | 2025-09-12 | 7
creating catagories and for the home page | Low Risk | Andrias | 100% | 2025-09-12 | 7
connecting login page with jpa backend | Med Risk | Andrias | 100% | 2025-09-12 | 7
work on gantt chart+flowchart | Low Risk | Selin | 100% | 2025-09-19 | 7
work on user registration | Low Risk | Andrias | 100% | 2025-09-19 | 7
design ERD for our entire database | Low Risk | Both | 100% | 2025-09-25 | 7
create the tables for the database | Med Risk | Andrias | 100% | 2025-09-25 | 7
build the html page for the breakfast category | High Risk | selin | 100% | 2025-10-10 | 7
build the html page for the lunch category | Low Risk | Selin | 100% | 2025-10-10 | 7
build the html page for the dinner category | Med Risk | selin | 100% | 2025-10-10 | 7
build the html page for the vegan category | Med Risk | Selin | 100% | 2025-10-10 | 5
build the html page for the vegetarian category | Med Risk | selin | 100% | 2025-10-10 | 5
add login validation | Med Risk | Andrias | 100% | 2025-10-01 | 5
insert new user record into Users table | Med Risk | Andrias | 100% | 2025-10-01 | 5
build the recipe detail page | High Risk | Selin | 100% | 2025-10-01 | 7
work on implementation of searching for recipes | High Risk | Selin | 100% | 2025-10-01 | 7
work on implemetation of adding recipes | High Risk | Selin | 100% | 2025-10-01 | 7
implemetation of deleting recipes | Low Risk | Selin | 100% | 2025-10-21 | 7
add form validation for recipe uplad form | Med Risk | Andrias | 100% | 2025-10-15 | 7
work on recipe upload to the website feature | High Risk | Selin | 100% | 2025-10-05 | 7
Integrate recipe feed with backend | High Risk | Andrias | 100% | 2025-10-22 | 7 | bar: 2025-12-14 to 2025-12-20
work on recipe detail page's backend | High Risk | Andrias | 100% | 2025-10-22 | 7
make the design of the pages better | High Risk | Selin | 100% | 2025-10-29 | 7
add at least 5 recipes for each category in the database | High Risk | Andrias | 100% | 2025-10-29 | 7
write unit tests for login service | High Risk | andrias | 100% | 2025-10-21 | 7
write unit tests for recipe upload service | High Risk | andrias | 100% | 2025-10-21 | 5
write unit tests for search functionality | High Risk | Andrias | 100% | 2025-10-21 | 5
write unit tests for recipe service | High Risk | Selin | 100% | 2025-10-21 | 5
add logging to all services | High Risk | Andrias | 100% | 2025-10-05 | 7
uploading images to our directory | Med Risk | Andrias | 100% | 2025-10-05 | 5
commenting the model classes | Low Risk | Andrias | 100% | 2025-10-10 | 3
fix holes on the service page | High Risk | Andrias | 100% | 2025-10-12 | 5
unit test for recipe service | Low Risk | andrias | 100% | 2025-10-15 | 5
fixing the homepage | Low Risk | andrias | 100% | 2025-10-25 | 5
creating about page and contact us page | Low Risk | andrias | 100% | 2025-10-22 | 7
linked the contact page with andrias's email | Low Risk | andrias | 100% | 2025-10-22 | 7
session handling | High Risk | andrias | 100% | 2025-10-22 | 7
developer documentation | High Risk | andrias | 90% | 2025-10-31 | 7
user documentation | Med Risk | selin | 0% | 2025-10-31 | 7
finish unit testing for all services | High Risk | both | 100% | 2025-10-31 | 7
add validation to deleting recipes | Med Risk | selin | 100% | 2025-10-31 | 7
user shouldn’t be able to post the same recipe twice | Med Risk | seln | 100% | 2025-10-31 | 4
password changing | High Risk | andrias | 100% | 2025-10-31 | 5
[6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | #VALUE! |  |  |  |  | November | [27 empty] | December
Scrolling increment: | 5 | time axis 2025-11-04 to 2025-12-29
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2025-11-04 | 3 | T: 2; W: 2; T: 2
Task 2 | Milestone |  |  | 2025-11-09 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2025-11-01 | 10
Task 4 | Milestone |  |  | 2025-11-24 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2025-11-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-11-10 | 13
Task 2 | On Track |  | 50% | 2025-11-12 | 9
Task 3 | Low Risk |  | 33% | 2025-11-17 | 11
Task 4 | Milestone |  |  | 2025-11-19 | 1 | bar: W
Task 5 |  |  |  | 2025-11-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-11-19 | 4
Task 2 | Med Risk |  |  | 2025-11-22 | 14
Task 3 | On Track |  |  | 2025-12-07 | 6
Task 4 | Goal |  |  | 2025-12-11 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2025-11-10 | 19
TITLE 4
Task 1 |  |  |  | 2025-12-14 | 15
Task 2 |  |  |  | 2025-12-28 | 5
Task 3 | Milestone |  |  | 2026-02-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | #VALUE! |  |  |  |  | November | [27 empty] | December
Scrolling increment: | 5 | time axis 2025-11-04 to 2025-12-29
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-11-04 to 2025-12-29
TITLE 1
Task 1 | Goal | Name | 25% | 2025-11-04 | 3 | 2025-11-04: 2; 2025-11-05: 2; 2025-11-06: 2
Task 2 | Milestone |  |  | 2025-11-09 | 1 | bar: 2025-11-09
Task 3 | Low Risk |  | 50% | 2025-11-01 | 10
Task 4 | Milestone |  |  | 2025-11-24 | 1 | bar: 2025-11-24
Task 5 | Med Risk |  | 10% | 2025-11-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-11-10 | 13
Task 2 | On Track |  | 50% | 2025-11-12 | 9
Task 3 | Low Risk |  | 33% | 2025-11-17 | 11
Task 4 | Milestone |  |  | 2025-11-19 | 1 | bar: 2025-11-19
Task 5 |  |  |  | 2025-11-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-11-19 | 4
Task 2 | Med Risk |  |  | 2025-11-22 | 14
Task 3 | On Track |  |  | 2025-12-07 | 6
Task 4 | Goal |  |  | 2025-12-11 | 3 | 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2
Task 5 | Low Risk |  |  | 2025-11-10 | 19
TITLE 4
Task 1 |  |  |  | 2025-12-14 | 15
Task 2 |  |  |  | 2025-12-28 | 5
Task 3 | Milestone |  |  | 2026-02-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one